## Sheet1
Subject | Effort 1-5 | Prioritiy 1-5 | Status | Name | Status Key
Documentation
App Functional Spec | 4 | 4 |  | Toby | Unassigned |  | Sprints
Full Project Functional Spec | 5 | 5 |  | Toby | Assigned
[5 empty] | Started |  | Jan8-Jan12 | Documentation
Main Pages |  |  |  |  | Partially Complete | 50%+ |  | Art + Design
Home page | 4 | 5 | 90% | Jerome | Complete |  |  | Prototyping Android
Item pages | 5 | 5 | 75% | Anon & Gus | Confirmed Complete
Cart Pages & Inventory |  |  | 65% | mairipaz |  |  | Jan22-Jan26 | Navigation Bar
Navigation Bar | [7 empty] | Prototyping iOS
Bar Functionality | 2 | 1 |  | Jerome
Bar Design | 1 | 3 |  | Jerome |  |  | Feb5-Feb9 | Main pages
Profile Button | 2 | 1 |  | Jerome |  |  |  | Admin Classes
Profile Button Functionality | 2 | 1 |  | Jerome |  |  |  | Admin Items
User Info | 2 | 2 |  | Jerome
Notification Button | 2 | 3 |  | Jerome |  |  | Feb26-Mar1 | Login Page
Notification Button Functionality | 3 | 4 |  | Jerome |  |  |  | Student Classes
Student Items
Admin Classes
Add Folder Button & Functionality | 2 | 1 |  |  |  |  | Mar11-Mar15 | Project Connection
Classroom "Folders" Functionality | 4 | 1
Editing & Deleting Folder Buttons | 3 | 2
New Admin/Student Buttons | 5 | 2
Student Folder Hopping | 3 | 3
Search Bar | 3 | 2 |  | Jerome
Admin Items
Item Card Display Functionality | 4 | 1 |  | gustavo
Item Functionality | 5 | 1 |  | gustavo
QR Code / Item ID Implementation | 4 | 2 | 75% | anon
Scroll Wheel | 2 | 2
Add Page Button | 5 | 4
Search Bar | 3 | 2 |  | Jerome
Student Classes
Restrict Normal Users | 3 | 3 | 80% | gustavo
Student Items
Restrict Normal Users | 3 | 3 | 80% | gustavo
Login Page
Login Page | 4 | 4
sign out & log in |  |  |  | Gus & Antonio
Prototyping Android
Setting up Xamarin | 3 | 5 |  | Gustavo + Toby
Setting up Android emulator | 3 | 5 |  | Gustavo
Setting up Git repository | 3 | 5 |  | Gustavo + Toby
Creating pages | 2 | 5 |  | Gustavo + Toby
Scan barcodes | 3 | 3 |  | Gustavo
Give copyright credit for barcode library | 1 | 5 | 90% in case it changes | Gustavo
Ask for camera permission | 3 | 4 |  | Gustavo
Style testing | 4 | 2 |  | Gustavo
Buttons testing | 1 | 3 |  | Gustavo
Navigation bar testing | 3 | 3 |  | Gustavo
Github Repository | 4 | 4 |  | Gustavo + Toby
Prototyping iOS
Setting up Xamarin | 3 | 5 |  | Anon
Setting up iOS emulator | 3 | 5 |  | Anon
Setting up Git repository | 3 | 5 |  | Anon
Creating pages | 2 | 5 |  | Anon
Scan barcodes | 3 | 3 |  | Anon
Give copyright credit for barcode library | 1 | 5 |  | Anon
Ask for camera permission | 3 | 4 |  | Anon
Style testing | 4 | 2 |  | Anon
Buttons testing | 1 | 3 |  | Anon
Navigation bar testing | 3 | 3 |  | Anon
Art + Design
Mockups | 5 | 4 |  | Jerome + Mairipaz
Icon design | 3 | 4 |  | Mairipaz
Layout prototyping | 4 | 1 |  | Mairipaz
Project Connection
Database communication | 4 | 5 | 80% | Antonio
Uploading project to server | 4 | 5 |  | Antonio
downloadable mobile app from link | 4 | 5 |  | Antonio