## Sheet1
Subject | Description | Sprint | Effort ¦ 1-10 | Prioritiy ¦ 1-10 | Time | Status | Name |  |  | Status Key
Unassigned
Prototyping | [9 empty] | Assigned
SQL- Node connector |  | - | 4 | 1 | 2 Hours |  | Antonio |  |  | Started
Server Research |  | - | 6 | 1 | 3 Days |  | Antonio |  |  | Partially Coded | 50%
Database research |  | - | 6 | 1 | 3 Days |  | Antonio + TJ |  |  | Code Complete
Server API - No DB |  | Sprint 1, Week 1 | 8 | 2 | 2 Days |  | Antonio + TJ |  |  | Testing | 35%
Server API - DB |  | Sprint 2, Week 1 | 9 | 3 | 10 Days | 90% | Antonio + TJ |  |  | Test Complete
KTProg connection |  |  |  |  | 1 Day | 60% | TJ |  |  | Needs Other Work
Web-Hosting platform |  |  |  |  | 1 Day |  | TJ |  |  | Cancelled
App connection |  |  |  |  | 3 Days |  | Antonio
Notes:
------------------------------------------------------------------------
Sprint 2 is dynamic support
Database Design | [7 empty] | Antonio integrates to web in sprint 2
Table Layout |  |  | 6 | 1 | - already done |  | TJ + Gordon | TJ is dynamic support in sprint 2
SQL init file |  | Sprint 1, Week 1 | 2 | 3 | 3 hours |  | Gordon | Gordon integrates to app in sprint 2
Working server-side database |  | Sprint 1, Week 2 | 4 | 4 | 5 hours |  | Antonio
Routines
Routine List |  |  | 5 | 1 | 1 Day |  | TJ + Gordon
Routine Implementations |  | Sprint 1, Week 2 | 9 | 4 | 1 Week | 90% | TJ, Gordon