## Sheet1
Subject | Description | Effort ¦ 1-10 | Prioritiy ¦ 1-10 | Week ¦ 1-4 | Time | Status | Name | Status Key
Unassigned
Navigation Bar | [7 empty] | Assigned
Bar Functionality | Adding the navigation bar & switching pages with "Classes & Items" button | 4 | 1 | Week 1 | 2 Hours |  | Lara+Jack+Jayden | Started
Bar Design | Design to help fill out empty space on top of hot bar, idea is already in place for what it'll look like | 2 | 5 | Week 1 | 1-2 Hours |  | Wemerson | Partially Coded | 50% | Example
Profile Button | Adding profile button in the top right | 3 | 2 | Week 1 | 1 Hour |  | Jack+Jayden | Code Complete
Profile Button Functionality | Pressing button should cause slideout of user info | 5 | 2 | Week 1 | 1-2 Hours |  | Jack | Testing | 35% | Example
User Info | Deciding on what the slideout contains & adding logout button | 5 | 3 | Week 1 | 1 Hour |  | Lara | Test Complete
Hide Password | Have the password hidden on the info slide, add a button that reveals password | 4 | 5 | Week 1 | 1 Hour |  | Jayden
Logout Button Functionality | Pressing button should cause user to logout & go to logout page | 7 | 3 | Week 2 | 2-3 Hours | 100% | Jack
Notification Design | Create design of notification button depending on the amount of notifications, example in "A-Class 1/3" | 4 | 5 | Week 2 | 1+ Hours |  | Wemerson
Notification Button | Slides out a list of notifications, depending on the type of user should alert for students who didn't turn in item / user themself didn't turn in item | 6 | 8 | Week 3 | 1-2 Hours |  | Lara
Notification Button Change Implementation | Implement the designs to actually change upon recieving notifications | 9 | 8 | Week 3 | 4 Hours |  | Group
Admin Classes
Add Folder Button & Functionality | Should be able to create a new class folder where students can be placed, example in pages 1 & 3 of "A-Classes" | 5 | 1 | Week 1 | 2 Hours |  | Reilly
Add Folder Button & Functionality | Clicking on a folder should bring out a list of users, clicking again should retract the list | 8 | 2 | Week 1 | 1-3 Hours |  | Reilly
Scroll Wheel | Add a scrollwheel that lets you browse inbetween folders | 4 | 5 | Week 1 | 1 Hours |  | Wemerson + Jayden
Folder Buttons | Clicking on the three dots should bring out two more buttons for editing and deleting | 4 | 4 | Week 1 | 1-2 Hours |  | Reilly + Jack
Editing & Deleting Folder Buttons | Adding functionality to edit and delete button from the folder | 6 | 4 | Week 1 | 2-3 Hours |  | Reilly
New Admin/Student Buttons | Should create a new account & should appear in correct class | 10 | 3 | Week 2 | 3+ Hours |  | Reilly
Student Folder Hopping | Admins should be able to drag & drop users to different classes | 7 | 6 | Week 3 | 2+ Hours |  | Reilly
Search Bar | Make admins able to search up other users & be able to edit their data | 6 | 3 | Week 4 | 2-3 Hours |  | Lara
Making Page Look Nice |  |  |  | Week 3 |  |  | Wemerson
Admin Items
Item Card Creation Menu | Button that shows all of the item details for creation | 7 | 1 | Week 1 | 2+ Hours |  | Lucas
Item Card Display Functionality | Item Card Creation should be able to add items to screen, should format & fit correctly & able to be dragged and dropped to organize | 8 | 1 | Week 1 | 3+ Hours | 50% | Lucas
Item Functionality | Clicking on card should bring up list of info, be able to be checked out and in, & be able to be edited & deleted. Ignore QR Code for now | 10 | 2 | Week 1 | 2-4 Hours |  | Group
Scroll Wheel | Same for Admin Classes | 4 | 4 | Week 1 | 1 Hour |  | Wemerson + Jayden
QR Code / Item ID Implementation | Implement the QR code into checkout & returning item | 9 | 3 | Week 2 | ? |  | Reilly
Add Page Button | Full Explanation in "Admin Items 2/2" | 10 | 9 | Week 3 | 4-5 Hours |  | Group
Search Bar | Make admins able to search up Items | 6 | 3 | Week 4 | 2-3 Hours |  | Lara
Student Classes
Restrict Normal Users | Make students unable to edit anyting outside of their own data | 5 | 5 | Week 3 | 2 Hours |  | Group
Student Items
Restrict Normal Users | Make students only able to checkout & return items, make sure they cannot edit any items | 5 | 5 | Week 3 | 2 Hours |  | Group
Login Page
Login Page | Let users sign into their account | 8 | 3 | Week 1 | 1-3 Hours |  | Jayden+Jack
Misc
Printing Barcode | making doc to decide how we will print barcodes | 3 | 1 | Week 1 | ? |  | Lara/Reilly
Broken(jack):
login fixed
add button
class & item button